## PS WCCA Task List
Sample Power Supply WCCA Buss Voltage Range: Guidelines: |  |  |  | PROPRIETARY AND CONFIDENTIAL TO AEi SYSTEMS Copyright AEI SYSTEMS, LLC 2004-2017 All Rights Reserved |  |  | Analysis Information Temperature Range: -TBD - +TBD, Delta TBD C Radiation Environment: TBDkRad, TBD Neutron
Specifications, Requirements, Design Objectives | R# | Spec. Para. # | Risk - H or L | Requirement/Specification | Results: (Nominal, BOL) | EOL Results: RSS-EVA, EVA) | Analysis Description | Analysis Method | Data Needs Testing Models
MODULE 1 – High Risk /AC Analysis
Stability - Gain and Phase Margin & Negative Input Impedance | 1 | [6 empty] | Monte Carlo
Conducted Susceptibility - CS01 | 2 | [6 empty] | Monte Carlo
Input Conducted Emissions - CE03 | 3 | [6 empty] | Sensitivity/SPICE
Input Filter - Damping, Attenuation | 4 | [6 empty] | Monte Carlo
Input Under Voltage ON/OFF threshold/ Latch off, no oscillations | 5 | [6 empty] | Sensitivity/SPICE
Output Ripple | 6 | [6 empty] | Mathcad
Switching Frequency Tolerance including Sync | 7 | [6 empty] | Sensitivity/SPICE
Efficiency | 8 | [6 empty] | Sensitivity/SPICE
High Risk Analysis Peer Review
MODULE 2 – DC Analysis
Vbias Voltage Regulation | 9 | [6 empty] | Sensitivity/SPICE
Primary Overcurrent Trip Thresholds | 10 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Short ckt analysis/Turn off - (survival) | 11 | [6 empty] | Monte Carlo
Output Overvoltage | 12 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Isolation Resistance and Capacitance | 13 | [6 empty] | Sensitivity/SPICE
ON Command Interface, Logic 1, Logic 0 thresholds | 14 | [6 empty] | Sensitivity or Parametric EVA/SPICE
OFF Command Interface, Logic 1, Logic 0 thresholds | 15 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Telemetry | 16 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Temperature Monitor telemetry impedance, failure, etc. | 17 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Buss Off State Leakage Current | 18 | [6 empty] | Sensitivity/SPICE
DC Analysis Peer Review
MODULE 3 – Time Domain Analysis - Transients
Load Step (Natural and Forced Responses) | 19 | [6 empty] | Monte Carlo
Output Response Buss Transient (Main Bus Power Fault Response, worst case over/undervoltage rate of change) | 20 | [6 empty] | Monte Carlo
Input UV/ Output Response to Buss Transient CS06 | 21 | [6 empty] | Monte Carlo
Buss Inrush Current due to Buss dv/dt, Input Short, Rate of Change | 22 | [6 empty] | Monte Carlo
Time Domain Analysis Peer Review
MODULE 4 – Time Domain Analysis – On/Off Command Analysis
On/Off Command turn on Overshoot, Turnon Time, Slew Rate, Delay, Inrush | 23 | [6 empty] | Monte Carlo
On/Off Command noise immunity - damped 1Mz sinusoidal | 24 | [6 empty] | Monte Carlo
Simultaneous On/Off commands | 25 | [6 empty] | Monte Carlo
Time Domain Analysis Peer Review
MODULE 5 – For EACH Output Voltage on a multiple output converter
Output Voltage Regulation , over line, load,etc | 26 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Output Over Voltage Failure / Protection | 27 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Magnetics Characteristics | 28 | [6 empty] | Parametric EVA
Power Sequencing | 29 | [6 empty] | Parametric EVA/SPICE
SEU and Prompt Dose, SET | 30 | [6 empty] | Parametric EVA/SPICE
Peer Review
MODULE 7 – Part Analyses
BJT Leakage and SOA | 31 | [6 empty] | Sensitivity or Parametric EVA/SPICE
FET SOA | 32 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Gate Drive Analysis | 33 | [6 empty] | Sensitivity or Parametric EVA/SPICE
min hFE | 34 | [6 empty] | Sensitivity or Parametric EVA/SPICE
Optocoupler CTR and Leakage | 35 | [6 empty] | Monte Carlo
Opamp Stability, Loading and Common Mode | 36 | [6 empty] | Monte Carlo
High Risk Analysis Peer Review
MODULE 8 – Other Analyses
Nominal Stress
Stress Based MTBF
FMECA
Worst Case Stress
Transient Stress
Peer Review

## Linear Regulator WCCA Task List
[14 empty] | REPORT DATE | 2017-06-18
LDO - Linear Regulator WCCA | [6 empty] | % Complete | [6 empty] | Planned |  | Actuals |  |  |  | Copyright AEI SYSTEMS, LLC 2004-2017 All Rights Reserved | Temperature Range: [-55 - +85], Delta [60C] | Radiation Environment: [100kRAD, No Neutron] | Misson Life [15] Years
Specifications, Requirements, Design Objectives | R# | Document Para. # | Risk - H or L | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | Start Date | End Date | Start Date | End Date | Responsible Engr | Compliance | Requirement | Status: (Nominal, BOL) | Status: (EOL, RSS-RSS, EOL EVA) | Analysis Description
VRGxxxxx
MODULE 1 – Tolerance Analysis
Stability - Gain and Phase Margin | 1 | [18 empty] | PM > 30 degrees GM > 12dB |  |  | Monte Carlo
Step Load | 2 | [21 empty] | Monte Carlo
Conducted Susceptibility - CS/Ripple Rejection | 3 | [21 empty] | Monte Carlo
Shutdown Threshold | 4 | [21 empty] | Mathcad
Headroom | 5 | [18 empty] | Headroom > Dropout Voltage |  |  | Mathcad
Output Voltage Regulation , over line, load,etc | 6 | [21 empty] | Mathcad
Short ckt analysis/Turn off - (survival) | 7 | [21 empty] | Monte Carlo
Over Current Limit | 8 | [21 empty] | Monte Carlo
Startup | 9 | [21 empty] | Monte Carlo
Optional: PSRR | 10 | [21 empty] | Monte Carlo
Optional: Reverse Transfer | 11 | [21 empty] | Monte Carlo
Peer Review
MODULE 2 – Other SDRLS
Stress and Derating Analysis - Nominal
Stress and Derating Analysis - Worst Case
Peer Review

## Analysis Data Check List
Program Name | Copyright AEI SYSTEMS, LLC 2004-2017 All Rights Reserved | Regulator #1 |  | Regulator #2 |  | Regulator #n
Schematic (MUST include ALL loads and load circuitry in all paths)
Bill of Materials (MUST include ALL load circuitry)
WCCA (Worst Case Circuit Analysis) |  | Part # | UNITS | Part # | UNITS | Part # | UNITS | Comments
| Nominal Input Voltage |  | V |  | V |  | V
| Minimum Input Voltage |  | V |  | V |  | V
| Maximum Input Voltage |  | V |  | V |  | V
| Input Voltage Transient |  | V |  | V |  | V
| Input Rise/Fall Times |  | S |  | S |  | S
| Input Source Impedance |  | Ohms |  | Ohms |  | Ohms
| Nominal Load Current |  | A |  | A |  | A
| Minimum Load Current |  | A |  | A |  | A
| Maximum load Current |  | A |  | A |  | A
| Load Transient |  | A |  | A |  | A
| Load Transient Rise/Fall Times |  | S |  | S |  | S
ENVIRONMENT | Nominal Case temperature |  | 'C |  | 'C |  | 'C
| Minimum Case Temperature |  | 'C |  | 'C |  | 'C
| Maximum Case Temperature |  | 'C |  | 'C |  | 'C
| Radiation Environment 1 |  | Krad |  | Krad |  | Krad | TID
| Radiation Environment 2 |  | Krad |  | Krad |  | Krad | ELDRS
| Radiation Environment 3 | [6 empty] | NEUTRON
| SET Upset Times (Hi and Lo) |  | S |  | S |  | S
| Mission life |  | Years |  | Years |  | Years
REQUIREMENTS | Gain Margin | 10 | dB | 10 | dB | 10 | dB
| Phase Margin | 30 | Deg | 30 | Deg | 30 | Deg
| DC Regulation (combination line, load, initial tolerance) | ≤ 5 | % | ≤ 5 | % | ≤ 5 | %
| Current Limit | ≤ 5 | A | ≤ 5 | A | ≤ 5 | A
| Pass-Transistor Current Gain | Verify sufficient Drive exists |  | Verify sufficient Drive exists |  | Verify sufficient Drive exists
Other Requirements
Controlling Document (Aging, Radiation, etc.)
EOL Electrical requirements
Minimum Capacitor ESR
OTHER DOCUMENTS | Component Datasheets, SCDs
Bench Test Data (stablity, step load, etc.)
Derating Analysis (Nominal Stress) |  |  | UNITS |  | UNITS |  | UNITS | Comments
| Nominal Input Voltage |  | V |  | V |  | V
| Minimum Input Voltage |  | V |  | V |  | V
| Maximum Input Voltage |  | V |  | V |  | V
| Input Voltage Transient |  | V |  | V |  | V
| Nominal Load Current |  | A |  | A |  | A
| Minimum Load Current |  | A |  | A |  | A
| Maximum load Current |  | A |  | A |  | A
| Load Transient |  | A |  | A |  | A
| Maximum Case temperature |  | 'C |  | 'C |  | 'C
| Controlling Document | Per SCD |  | Per SCD |  | Per SCD
Worst Case Stress Analysis |  |  | UNITS |  | UNITS |  | UNITS | Comments
| Nominal Input Voltage |  | V |  | V |  | V
| Minimum Input Voltage |  | V |  | V |  | V
| Maximum Input Voltage |  | V |  | V |  | V
| Input Voltage Transients |  | V |  | V |  | V
| Nominal Load Current |  | A |  | A |  | A
| Minimum Load Current |  | A |  | A |  | A
| Maximum load Current |  | A |  | A |  | A
| Load Transient |  | A |  | A |  | A
| Maximum Case temperature |  | 'C |  | 'C |  | 'C
| Controlling Document | Per SCD |  | Per SCD |  | Per SCD

## Condensed Priorty
Reasons to Perform Worst Case Analysis
Need | Reason | Risk | Priority
Design Verification and Reliability | To verify circuit operation and quantify the operating margins over part tolerances and operating conditions - Will the circuit perform its functions and meet specifications/To quantify the risk | H/L
To improve performance - to determine the sensitivity of components to certain characteristics or tolerances in order to better optimize/understand a design and what drives performance
To verify that a circuit interfaces with another design properly
To determine the impact of part failures or out of tolerance modes
Test Cost Reduction | To evaluate performance aspects that are difficult, expensive or impossible to measure (i.e. determine the impact of input stimulus and output loading so as not to damage hardware)
To set ATP limits
To verify SATs/SITs and if they are needed/what their limits should be
To reduce the amount and scope of testing
Parts Assessment | To determine if a part is suitable (too cheap, too expensive) or if a New Technology can be used
To support/set critical parameters and SCD requirements/screening definition
To perform Single Event Transient (SET) analyses
Schedule, Cost, or Contractual Risk Reduction | To reduce board spins - determine the impact of late stage design or part changes
To verify changes to heritage circuits
To obtain better insurance rates or reduce contractual liabilities
To avoid a catastrophic or costly incident
Definitions
Tolerances | Initial (manufacturing), Temperature, Environmental (Testing (thermal cycle, Vib., Hum., Age, Radiation)
BOL | Beginning-of-Life - Initial and Temperature Tolerances
EOL | End-of-Life - All Tolerances
EVA | Extreme Value Analysis, Also refers to Tolerances as in "all of them stacked up"
RSS | Root Square Sum - can be applied to "random" tolerances or errors from each component